## Slide 1: PRINCE Full Lifecycle
A walkthrough of a simple project

## Slide 2: The Project Mandate
Came from the corporate as competitors are gaining on us.
To create an iPhone APP
  For new and existing customers
  Order our services on-line
  Includes a fun game
  Marketing materials to publicise the APP
You have just 12 weeks
£5,000 no more
Must integrate with company refresh project
View the full
Project Mandate

## Slide 3: The planned project structure
Start Up
Initiation
Stage
Controlling 1st
Delivery Stage
Controlling Final
Delivery Stage
1st Stage
Boundary
Final Stage
Boundary
Close
Project
Realise
Benefits
Managing the
Delivery of:
APP Specifying
Local Developer
Marketing plan
Managing Delivery of:
APP Code for Sales
& Game
Marketing Materials
Trials with customers
Click on one of the links to view the files for APP Project
An Exception Occurred
A Risk was managed
An Issue Occurred
Directing a Project

## Slide 4: Starting Up APP Project
Appoint the Executive
And Project Manager
Daily Log
Click on one of the links to view the files for the APP Project
Capture Previous
Lessons
Lessons Log
Create outline
Business Case
outline Business Case
Project Product
Description
Select the Project Approach
And Assemble the Project Brief
Project
Brief
Design and Appoint the
Project Management Team
Plan the
Initiation Stage
Stage Plan
For Initiation

## Slide 5: Initiating APP Project
Create the Risk
Management Strategy
Create the Quality
Management Strategy
Create the Configuration
Management Strategy
Risk Management Strategy
Risk Register
Create the Communications
Management Strategy
Quality Mgt Strategy
Quality Register
Configuration Mgt Strategy
Issue Register
Commuunication Mgt Strategy
Create the Project Plan
Project Plan
Create the Project Controls
Refine the Business Case
Assemble the PID
Detailed Business case
Benefit review Plan
PID
Daily Log - updated

## Slide 6: Project Planning

## Slide 7: 1st Stage Boundary for APP Project
Plan the next Stage
Stage Plan
Product Descriptions
Configuration Item Records
Update the Project Plan
Project Plan
Update the Business Case
Business Case
Report Stage End
End Stage Report

## Slide 8: Stage Planning

## Slide 9: Controlling the 1st Delivery Stage
Authorise a Work
Package
Work Package
Review Work
Package Status
Checkpoint Report
Receive a completed
Work Package
Completed Work Package
Issue Report
Capture and Examine
Issues and Risks
Review Stage
Status
Take Corrective
Action
Escalate
Issues and Risks
Report Highlights
Highlight Report

## Slide 10: Managing the Marketing Plan Product Delivery
Agree the Work
Package
Work Package
Execute the Work
Package
Checkpoint Report
Deliver a completed
Work Package
Completed Work Package
Product Description
Quality Register

## Slide 11: Final Stage Boundary for APP Project
Plan the next Stage
Stage Plan
Product Descriptions
Configuration Item Records
Update the Project Plan
Project Plan
Update the Business Case
Business Case
Report Stage End
End Stage Report

## Slide 12: Controlling the Final Delivery Stage
Authorise a Work
Package
Work Package
Review Work
Package Status
Checkpoint Report
Receive a completed
Work Package
Completed Work Package
Issue Report
Capture and Examine
Issues and Risks
Review Stage
Status
Take Corrective
Action
Escalate
Issues and Risks
Report Highlights
Exception Report
Highlight Report

## Slide 13: Managing the APP Code Product Delivery
Agree the Work
Package
Work Package
Execute the Work
Package
Issue Report
Deliver a completed
Work Package
Completed Work Package
Product Description

## Slide 14: Dealing with an Exception
Capture the
Issue
Issue Report
Issue Register
Examine the
Impact
Propose Options
Take Corrective
Action
Issue Register
Exception Report
Decide
Informal
Formal
Daily Log
Ad-hoc Project Board Direction

## Slide 15: Managing a Risk

## Slide 16: Exception Stage Boundary for APP Project
Plan the Exception
Exception Plan
Product Descriptions
Configuration Item Records
Update the Project Plan
Project Plan
Update the Business Case
Business Case
Report Stage End
End Stage Report

## Slide 17: Project Board Decisions
Authorise Initiation
Project Brief
Initiation Stage Plan
Authorise Project
Project Initiation
Documentation
Benefit Review Plan
Authorise a Stage or
Exception Plan
Updated PID
Stage Plan
Exception Plan
or
Ad hoc Direction
Exception/issue Report
Highlight Report
Authorise
Project
Closure
End Project Report
Benefit Review Plan

## Slide 18: Closing the APP Project